# Appendices

### Appendix 1: Requirements Table

| Requirement | Source | Description | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| Motorola 68k CPU | Transcript p.8 | System must use a CPU from the Motorola 68k family | High | None |
| Minimum 512KB RAM | Transcript p.8 | System must include at least 512KB of memory | High | None |
| Storage Drive(s) | Transcript p.8-9 | System must include storage capability | High | None |
| External Keyboard | Transcript p.10 | System must support external keyboard | High | Expansion Capability |
| Serial Port(s) | Transcript p.10 | System must include serial connectivity | High | None |
| Industry Compatibility | Transcript p.9 | System must work with industry standards | High | Storage Drive(s) |
| Expansion Capability | Transcript p.9 | System must support future expansion | Medium | None |
| HB/OS Operating System | Chapter 4, p.15-16 | System must run HB/OS to support bundled applications | High | None |
| EZ-Suite Compatibility | Chapter 3, p.12 | Must run EZ-Suite applications | High | HB/OS |
| Multiple OS Support | Transcript p.9-10 | System should support multiple operating systems | Medium | CPU, RAM |
| Performance | Implied | System must provide acceptable response times | Medium | CPU, RAM |
| Reliability | Implied | System must operate without frequent crashes | High | All components |

### Appendix 2: System Configuration Table

| Component | Selection | Price | Justification |
| --- | --- | --- | --- |
| CPU | 68000 16MHz | £15 | Required by EDC (Chapter 5.2: "At least a 68000 CPU") |
| RAM | 4 × 128KB chips | £60 | 512KB total RAM requirement |
| ROM | 32KB | £6 | Sufficient for boot loader and OS |
| Glue Logic | G1-G4 set | £20 | Required for system integration |
| Display | Standard DISP | £12 | Basic display capabilities |
| Storage | 3.5" floppy | £20 | Industry-standard drive (Chapter 5.2) |
| I/O | SC100 (dual serial) | £7 | Provides two serial ports (Chapter 5.2) |
| I/O | SC150 (keyboard/joystick) | £6 | External keyboard support (Chapter 5.2) |
| Power | Standard PSU | £10 | Required component |
| Case | Desktop | £25 | As per Chapter 5.1 |
| Pro Expansion Board | Standard | £15 | Provides SCSI and upgrade path (Chapter 5.3) |
| EM Shielding | Custom | £4 | Addresses interference issues (Chapter 5.1) |
| Hardware Total |  | £200 |  |
| Software Licensing | Various | £70 | HB/OS (£0), MccOS (£20), TeleBASIC (£25), EZ-Suite (£25) |
| TotalCost |  | £270 |  |

### Appendix 3: Phase 1: Design and Planning (Dec 1982 - Feb 1983, 61 working days)

- Timeline: December 1, 1982 - February 28, 1983 (21+20+20 working days)

- Hardware/software architecture design

- Component selection and sourcing

- Resource allocation: £60,950 (including 15% contingency)

- Stage Gate: Design Review (February 28, 1983)

| Role | Daily Rate | Key Deliverables | Days | Cost |
| --- | --- | --- | --- | --- |
| Hardware Architect | £250 | • System architecture specification • Complete circuit diagrams • PCB design specs • Components list with vendors • Design review documentation | 40 | £10,000 |
| Software Architect | £300 | • OS integration specification • Boot architecture document • Dual-boot technical specification • Memory architecture document • Driver interface specification | 45 | £13,500 |
| Hardware Engineers (2) | £175 each | • Component evaluation report • Prototype circuit sections • EM mitigation design • Expansion interface design | 25 each | £8,750 |
| Software Engineers (2) | £195 each | • Boot ROM architecture • OS compatibility report • Driver development plan • Test plan document | 25 each | £9,750 |
| Project Manager | £275 | • Master project plan • Vendor contracts • Resource allocation plan • Risk register • EDC communication plan | 40 | £11,000 |
| Phase 1 Subtotal |  | £53,000 |  |  |
| Contingency (15%) |  | £7,950 |  |  |
| Phase 1 Total |  | £60,950 |  |  |

### Appendix 4: Phase 2: Prototyping and Testing (Mar 1983 - Jul 1983, 105 working days)

- Timeline: March 1, 1983 - July 29, 1983 (23+19+20+22+21 working days)

- Hardware prototype construction

- Software development and integration

- Testing: Unit, integration and system testing

- Resource allocation with parallel task work: £130,784 (including 15% contingency)

- Stage Gate: Production Approval (July 29, 1983)

| Role | Daily Rate | Key Deliverables | Days | Cost |
| --- | --- | --- | --- | --- |
| Hardware Architect | £250 | • Functional hardware prototype • Optimised circuit designs • EM shield specifications • Optimised ULA designs • Production specifications | 60 | £15,000 |
| Software Architect | £300 | • Functioning dual OS system • Working TeleBASIC on MccOS • Memory management subsystem • GUI design specification • Integration test reports | 70 | £21,000 |
| Hardware Engineers (2) | £175each | • Multiple hardware prototypes • Component test results • Assembled circuit boards • Debug reports and fixes • Production test jigs | 70 each | £24,500 |
| Software Engineers (2) | £195 each | • Functioning boot ROM • Working device drivers • Integration test results • TeleBASIC integration • Expansion board drivers | 65 each | £25,350 |
| Project Manager | £275 | • Milestone progress reports • Test plan execution • Component supply chain • QA procedures document • Production plan | 65 | £17,875 |
| Project Analyst (Agency) | £250 | • Detailed test plans • Quality standards document• UAT completion report • Requirements compliance report | 40 | £10,000 |
| Phase 2 Subtotal |  | £113,725 |  |  |
| Contingency (15%) |  | £17,059 |  |  |
| Phase 2 Total |  | £130,784 |  |  |

### Appendix 5: Phase 3: Production (Aug 1983 - Dec 1983, 107 working days)

- Timeline: August 1, 1983 - December 31, 1983 (22+22+21+22+20 working days)

- Manufacturing setup and production

- Quality assurance

- Commercial units (Aug-Oct 1983): 800 units

- EDC units (Oct-Dec 1983): 2,000 units

- Resource allocation with parallel task work: £68,224 (including 15% contingency)

- Stage Gates:

  - Production Review 1 (25% - October 15, 1983)

  - Production Review 2 (50% - November 15, 1983)

  - Production Review 3 (75% - December 15, 1983)

| Role | Daily Rate | Deliverables | Days | Cost |
| --- | --- | --- | --- | --- |
| Hardware Architect | £250 | • Production line setup • QA procedures for production • Technical solutions document • Production-optimised designs | 30 | £7,500 |
| Software Architect | £300 | • Production OS image • Software release package • GEM implementation plan • Software QA documentation | 30 | £9,000 |
| Hardware Engineers (2) | £175 each | • 800 completed commercial units • 2,000 completed EDC units • Operational test jigs • Production yield reports | 40 each | £14,000 |
| Software Engineer | £195 | • Production software package • Automated installation system • Final device drivers • System diagnostic tools | 35 | £6,825 |
| Project Manager | £275 | • 800 commercial units schedule • 2,000 EDC units schedule • Delivery plan and execution • Commercial market entry plan • Resource utilisation reports | 80 | £22,000 |
| Phase 3 Subtotal |  | £59,325 |  |  |
| Contingency (15%) |  | £8,899 |  |  |
| Phase 3 Total |  | £68,224 |  |  |

Total Development Labour Costs: £259,958

### Appendix 6: Testing Plan

| Phase | Testing Type | Duration | Activities | Participants |
| --- | --- | --- | --- | --- |
| Design and Planning | Design Validation | Ongoing | Peer reviews and simulations to verify hardware schematics, software architecture, and component selection. | Hardware and Software Architects |
| Prototyping and Testing | Unit Testing | 6 weeks | Testing individual hardware components and software modules against functional requirements. | Hardware and Software Engineers |
|  | Integration Testing | 4 weeks | Verifying the interaction between hardware and software components. | Hardware and Software Engineers |
|  | System Testing | 5 weeks | Full system testing for performance, stress, and functionality benchmarks. | Project Manager, Hardware and Software Engineers |
|  | User Acceptance Testing | 2 weeks | Internal users testing the system against business requirements and usability. | All |
| Production | Quality Assurance | Ongoing | Random sample testing during production at 25%, 50%, and 75% milestones. | Hardware and Software Engineers |

### Appendix 7: Gherkin Specifications

Feature: Power on/off and restarting the system

Scenario: Power on

Given The computer is plugged in

When The on button is pressed

And The monitor is switched on

Then The computer will boot up into the operating system

Scenario: Power off

Given The computer is on

When The user clicks the power off button

Then The computer will power down

Scenario: Restart

Given The power is on

When The user clicks the Restart button

Then The system should power down

And The system should automatically power back on

Scenario: Log in

Given The power is on

When The login screen has loaded

And The user types in a username and Password

And The enter key is pressed

Then The computer will log the user in

Scenario: Log out

Given The power is on

And A user is logged in

When The user types 'log out' and their username

Then The user will be logged out

And The Computer will return to the login screen

Feature: Accessing and using applications

Scenario: Accessing EZ-Suite software

Given The computer is powered on

When The user clicks on the EZ-Suite application Icon

Then The applications will run

And Display a menu for the user to navigate

Scenario: Saving a Document in EZ-Suite

Given The computer is powered on

And Running the EZ-Suite software

When The user clicks the 'Save' Icon

Then The user can name the document

And The document will save to the Storage

Scenario: Loading a Document in EZ-Suite

Given The computer is powered on

And Running the EZ-Suite software

When The user clicks the 'Load' Icon

And selects the document they wish to open

Then The document will open

And be displayed on the screen

Scenario: Deleting a Document in EZ-Suite

Given The computer is powered on

And Running the EZ-Suite software

When The user clicks the 'delete' Icon

And Clicks on the name of the document

Then The document will be deleted

Scenario: Accessing the Emulator

Given The computer is powered on

When The user clicks on the Emulator Icon

Then The application will run

And Display a menu of games

Scenario: Closing the Emulator

Given The computer is powered on

And The Emulator is running

When The user clicks on the close Icon

Then The application will close

And The user will returned to the home screen

Feature: Connecting and disconnecting peripherals

Scenario: Connecting a Joystick

Given The computer is powered on

When The user plugs in a Joystick

Then The device will connect

And The user will be able to begin using the Joystick

Scenario: Disconnecting a Joystick

Given The computer is powered on

And A Joystick is connected

When The user clicks 'Eject input connection'

Then The Joystick will be disconnected

And The Joystick can be unplugged

Scenario: Connecting a Keyboard

Given The computer is powered on

When The user plugs in a Keyboard

Then The device will connect

And The user will be able to begin using the Keyboard

Scenario: Disconnecting a Keyboard

Given The computer is powered on

And A Keyboard is connected

When The user clicks 'Eject Keyboard'

Then The Keyboard will be disconnected

And The Keyboard can be unplugged

Scenario: Connecting a Printer

Given The computer is powered on

When The user plugs in a printer

Then The device will connect

And The user will be able to begin using the printer

Scenario: Using a Printer

Given The computer is powered on

And A Printer is connected

When The user clicks 'print'

Then A menu will appear with printing options

And When the user clicks 'print' the printing will start

Scenario: Disconnecting a Printer

Given The computer is powered on

And A Printer is connected

When The user clicks 'Eject Printer'

Then The Printer will be disconnected

And The Printer can be unplugged